## User Stories
As | I Should | So that
Admin | be able to create an admin and other employees | I can manage them
Admin | be able to login into the system | I can perform admin activities
Admin | be able to delete employees | I can remove employees from the system
Admin | be able to update employees records | I can update employe information in the system
Admin | be able to view all employees in the system | I can view all the list of employees
Admin | be able to view individual employees in the system | I can view their salary information and personal details
Admin | be able to createand assign leave to employees in the system | I can assign them to employees going on leave
Employee | be able to login into the system | I can perform access the system
Employee | be able to view my personal information | I can see my information
Employee | be able to update my information | I can update my information in the system
Employee | be able to check my leave status | I can view my leave status

## Sprints
Sprint | Use Case | Feature/User story | Weight | Resource | Expected Completion Date
ONE | Admin | be able to create an admin and other employees | 5 | Yusuf
| Admin | be able to login into the system | 5 | Yusuf
| Admin | be able to delete employees | 4 | Yusuf
| Admin | be able to update employees records | 4 | Yusuf
| Admin | be able to view all employees in the system | 5 | Yusuf
| Admin | be able to view individual employees in the system | 4 | Yusuf
| Admin | be able to createand assign leave to employees in the system | 3 | Yusuf
TWO | Employee | be able to login into the system | 5 | Yusuf
| Employee | be able to view my personal information | 3 | Yusuf
| Employee | be able to update my information | 3 | Yusuf
| Employee | be able to check my leave status | 2 | Yusuf
| Employee | be able to request for leave | 2 | Yusuf

## Release
Release | Will have | Might have | Wont have
ONE | Admin login into the system
Admin creating other admins
Admin creating other employees
Admin viewing the list of employees
Admin updating employee information
Admin viewing individual employee
Admin creating leave
Admin assigning leave to employee
TWO | Employee login into the system | Request for leave
Employee view their profile
Employee update their profile information
Employee checking leave status